# Purpose

The purpose of the transfer meeting is to ensure a complete and uniform transfer of all project data to a next phase.

# Scope

This procedure is applicable for all projects

# Explanation of terms

None.

# Interface documentation

- Procedure Kick Off Meeting [QU-P-18]

- Procedure Project File [QU-P-05]

# Responsibilities

The table below indicates the organiser of the Transfer Meeting, the minimum attendance and the distribution.

| Transfer meeting | Organiser of meeting & agenda | Proposed attendance by | Distribution |
| --- | --- | --- | --- |
| Marketing & Business Development to Tender & Negotiation | Area/ subs manager | Area manager/ subsidiary manager, tender manager, estimator | Participants + PE dept head |
| Tender kick off meeting |  | See procedure kick off meeting |  |
| Tender & Negotiation to Work Preparation. | Area/ Subs manager | Tender team: Tender manager, estimator, area manager/ subsidiary manager, ad hoc staff, department related experts. Work preparation team: Project manager, work preparation team | Participants + PE department head |
| Project kick off meeting with Partners | Area/ subs manager | See procedure kick off meetings |  |
| Internal project kick off meeting | Area/ subs manager | See procedure kick off meetings |  |
| Work package kick off meetings | Project manager | See procedure kick off meetings | Participants + area/ subs managers |
| Work Execution to Liability & After Sales | Project manager | Project manager, area/ subs manager, key maintenance personnel | Participants |

# Description

## General

The organiser is responsible for organising the transfer meeting at the earliest opportunity. He shall ensure that all documents gathered during the previous phase are transferred in a logic and orderly manner with the necessary explanations.

Some typical items for the establishment of the agenda of the Transfer Meetings are included in the attachment.

# Attached documentation

- Attachment: Typical agenda items for Transfer Meetings

Attachment: Typical agenda items for Transfer Meetings

| Marketing & Business Development to Tender & Negotiation | Tender & Negotiation to Work Preparation | Kick off meeting work packages | Work Execution to Liability & After Sales |
| --- | --- | --- | --- |
| - The Project File - Project history - Budget estimate [where applicable] - Funding & payment ideas - Pre-qualification - Involved parties - Client, consultants, project managers, preferred subcontractors, funding agency] - Status of correspondence - with Client, engineer - partners, subcontractors - Minutes of meetings - with Client - with others - Agreements - pre-bid agreement including important j.v. agreements - memorandum of understanding - expression of interest of potential subcontractors - Tender documents - Invitation to Tender - Bid Documents [ Mom to be produced and distributed] | - The Project File - Project history - The tender submission - Liquidity - Risk analysis - Applicable codes, standards, specifications - The results of the negotiations - Finance, payment terms - The involved parties - Key project team - Status of correspondence - Minutes of meetings - Agreements [contract, consortium/ j.v. agreement] - Design aspects - Verification of aspects to be designed - Design planing - Approval procedure - Auxiliaries - Work methods & take off - Document deliverable list - Overall work schedule - Design schedule - Procurement schedule - Personnel schedule with chart - Equipment schedule - Mobilisation schedule - Financing schedule - Subcontractors and discounts during tender - Technical advise - Concrete, steel, piping, etc. - Status project plan including safety matters - Required permits - The critical activities for the next weeks [ MoM to be produces and distributed] | - The transfer between the work preparation and work execution phase is by means of a number of kick off meetings about work packages. - The agenda of the kick off meetings is described in the procedure kick off meetings. [ MoM to be produced and distributed] | - The Project File - Demobilisation - Project after sales plan - Status close out report - Liability to Client [project maintenance organisation] - Status retrieval bonds & guarantees - Status completion certificate - Status final account with Client, Partners, Subcontractors and suppliers - Final documentation - Taking over certificate - Punch list - Any other outstanding items [ MoM to be produced and distributed] . |