# Purpose

The purpose of the kick-off meeting is to transfer information to ensure a common understanding of the requirements of the Contract.

# Scope

This procedure is applicable for all tenders and projects.

# Explanation of terms

None.

# Interface documentation

- Procedure Transfer Meetings [QU-P-10]

- Procedure Project File [QU-P-05]

# Responsibilities

Responsibilities are indicated in table 1, which shows the organiser of the kick-off meetings, the minimum attendance and the distribution

Table 1.

| Kick off meeting | Organiser of meeting & agenda | Proposed attendance by | Distribution |
| --- | --- | --- | --- |
| Tender kick- off meeting | Area Manager | Area Manager, Tender Manager, Head of PE Department, Estimator, Area Controller and relevant personnel from other staff departments as would be required, such as: - Purchaser, for sourcing advises both locally and foreign. - Transport co-ordinator [lead times special transports]. - Plant engineer [equipment and special auxiliaries]. - Contractual Advisor for contractual matters. - Safety manager for safety input. - Representative from the Insurance Dept. of HBG | Participants |
| Internal project kick off meeting | Area Manager | Area Manager, Project Manager, Head of PE Department, Tender Manager, Estimator, Area Controller, Work Preparation Engineer, Scheduling Engineer, Manager of Design and any other key project personnel + relevant personnel from other staff departments, such as: Purchaser, Expeditor, Transport co-ordinator, Plant Engineer, Contractual Advisor, Quality Manager and Safety Manager. | Participants |
| J.V. Partner Project Kick Off Meeting | Area Manager | Area Manager, Project Manager, Manager of Design + any relevant key project personnel + relevant key personnel from partners | Participants |
| Design Kick Off Meeting | Manager of Design | Area Manager, Project Manager, Manager of Design + any relevant key project personnel + relevant key personnel from design subcontractor | Participants |
| Work package kick off meetings | Project manager | Project Manager, Construction Manager, involved Work Preparation Engineer, Chief Surveyor, relevant Superintendent / Supervisors, Quality and Safety Personnel + relevant key personnel of subcontractor[s] and Client [if desired] | Participants + area/ subs managers |
| Kick off meeting with Client | Project Manager | Key staff from Client and Contractor | Client + Key staff + Area Manager |

# Description

- General: The organiser is responsible for organising the kick off meeting at the earliest possible opportunity.

- To assist the organiser in establishing the agenda of the kick off meetings, some typical items to be discussed are included in the attachment.

- The agenda for the kick off meeting with the Client will in general be established by the Client. The Project Manager however shall add relevant aspects, which shall be discussed and / or agreed.

# Attached documentation

- Typical agenda items for kick off meetings

Attachment: Typical agenda items for the 'Tender kick-off meeting'

| Tender kick-off meeting |  |
| --- | --- |
| Agenda - Opening - Introduction of the attendees - Establish agenda - Introduction project: - Overview drawing / location of project - Background to the project - General considerations for tendering - Scope of work - Expected competition - Review of TIS - Contractual set-up Consortium / JV matters: - Partner selection - Sub contracting strategy [designer, local subcontractors] - Pre-bid agreements - Tender cost split - Design contracts - Liability of designer [incl. PI cover] - Tender Budget Control measures - Tender process: - Tender time schedule [conforming bid / alternatives] - Tender organisation schedule / team composition - Tender Team Task Matrix - Tender information requirements - Tender Document Control - Tender review requirements - Tender cost monitoring system - Schedule of meeting incl. audits - Reporting structure - Bid Document compilation - Tender Evaluation / Closeout - Alternatives - Maximisation of local know-how as far as design, equipment, materials, subcontractors and staff. | - Detailed tender activities: - Technical work methods / Method Statements - Design aspects; Design brainstorm meeting for EPC Contracts - Site - IT-Matters (SAP or NON-SAP) - Estimating - Contractual / Financial conditions - Project financing issues - Insurance / Bonding - Currency aspects / taxation - Quality and Safety aspects - Plant & procurement - Lessons learned of similar projects - Further requirements as specified in the Instruction to Bidders [ITB] - Risk analyse: - Determination necessity and extend - Agreement on type of risk analyse [ Minutes of meeting to be produced and distributed] |

Attachment: Typical agenda items for remaining kick-off meetings

| Project kick-off meeting [internal][to advise SHANFARI TRADING AND FURNISHING CO. LLC organisation about new project] | Project kick-off meeting [with partners] | [Tender & Project] Design kick-off Meeting [with design subcontractor[s]] | Kick-off meeting work packages |
| --- | --- | --- | --- |
| - Opening - Introduction of the attendees - Overview drawing/ location of project - Project history - Detailed description of scope of work - The tender submission & negotiation - Finance, payment terms, advance payments - NCM, bonds, insurances - Contractual relationships & topics - Key project team - Overall work schedule - Work methods - Design matters - Procurement matters - Subcontract matters - Project control systems - Safety matters - Status project plan including safety matters - Initial work preparation schedule - Hand-outs: - Project description [ general, main project data, key contractual and financial matters, bonds, guarantees, warrantees, insurance and permits - Location sketch - Overall work schedule - Responsibility matrix - Critical activities next weeks [ Minutes of meeting to be produced and distributed] . | - Opening - Overview drawing / location of project - Project history - Detailed description of scope of work - The tender submission & negotiation - Finance, payment terms - Contractual relationships & topics - Key project team - Overall work schedule - Work methods - Design matters - Procurement matters - Subcontract matters - Project control systems - Safety matters - Status project plan including safety matters - Initial work preparation schedule - Ensure that the prepared and agreed JV agreement is signed, based on the tender agreement including the main project management tools agreed, such as [in the case of a consortium a project co-ordination procedure which includes: - Project document control system - Correspondence system - Budget & forecasting system - The underlying administrative system - IT systems - Decide on the complete contents of the Project Plan, based on the outline project plan during tender stage [if ready, sign the project plan]. - Hand-outs: - Project description [ general, main project data, key contractual and financial matters, bonds, guarantees, warrantees, insurance and permits - Location sketch - Overall work schedule - Responsibility matrix - Critical activities next weeks [ Minutes of meeting to be produced and distributed] | - Opening - Overview drawing / location of project - Project history - Detailed description of scope of total work - Contractual relationships & topics - Key project team - Overall work schedule - Work methods - Design scope - Important aspects: - The most economical design in conformance with specifications and safe working requirements. - Basis of design - A constructable design - Project Design Plan - Design schedule with interactions with others, importance of design freeze dates and concurrent delays - Engineering document schedule or CTR - Info and dates of data required from others - Standardise on available vendor specs. - Project Document Control System - Communication & reporting - Procurement matters and assistance required from design team - Subcontract matters and assistance required from design team - Cost influences [ Minutes of meeting to be produced and distributed] | - The transfer between the work preparation and work execution phase is by means of a number of kick off meetings about work packages. - The agenda of the kick off meetings is specific for the related work package. [Minutes of meeting to be produced and distributed] |