# Purpose

The purpose of a project plan is to enable that the contract requirements are met in a planned and controlled manner.

# Scope

Project Plans are mandatory within the SHANFARI TRADING AND FURNISHING CO. LLC organisation.

The users of this procedure are all staff.

This procedure is applicable for certain pre-qualifications for selected projects, all company controlled tenders and projects.

In cases where SHANFARI TRADING AND FURNISHING CO. LLC is a non-leading partner in a Joint Venture, the aim is to achieve at least a Quality and Safety standard comparable with SHANFARI TRADING AND FURNISHING CO. LLC’s own standard.

# Explanation of terms

Company controlled 	A tender/project where SHANFARI TRADING AND FURNISHING CO. LLC is the sponsor.

tender/project:

Outline Project Plan: 	An Outline of a Project Plan, used during pre-qualification and 		tender stage. This usually consists of an amended document [QU-	E-02] and a number of selected documents.

Outline Project 	An Outline of the Project Design Plan [PDP].

Design Plan:	[ the typical contents of a PDP are enclosed as attachment 1].

Project Plan:	A project specific Project Plan.

Project Design Plan: 	A project specific Project Design Plan.

# Interface documentation

- Draft Preliminary Project Plan [QU-E-02]

- Procedure pre-qualifications [PR-P-08]

- Procedure Partner Assessment [AR-P-06]

- Procedure Risk Analysis [PE-P-17]

# Responsibilities

During pre-qualification phase, the Area Managers are responsible for ensuring that agreements are made regarding the use of the major project management tools, to be implemented after project award.

During tender phase, the Area Managers are responsible for ensuring that agreements are made regarding the use of the above indicated outline project plans, to be implemented after project award.

The Project Manager is responsible that the Project Plan, including a schedule of deliverables, has been completed one month after start of Work Preparation or after the effective date of the Contract, whichever is the earliest.

In the case of a consortium [not an integrated joint venture] a project co-ordination plan is to be agreed with the consortium members, based on the contract and the typical project plan. The individual parties to work out their own project plan which shall comply with the co-ordination plan.

# Description

## Form of co-operation and structure of Co-ordination Plan / Project Plan

In the case of a consortium [not an integrated joint venture] SHANFARI TRADING AND FURNISHING CO. LLC shall endeavour to agree a project co-ordination plan with the consortium members, [based on the contract and the typical project plan]. Individual parties should work out their own project plan, which shall comply with the co-ordination plan requirements.

## During Pre-Qualification Phase

Depending on the form of co-operation between partners, a minimum number of relevant project management procedures [tools] and content lists, to be used after project award, need to be agreed during pre-qualification stage. This agreeing process can be in the form of assessing each others in-house project management tools and selecting the most suitable for the project. In this early stage the agreement document can be in the form of a co-ordination plan.

The pre-bid agreement should contain a clause that the tender design costs [internal as well as external] are to be handled as third party costs and are to be shared between the parties.

Project management tools requiring agreement are:

- For a consortium partner:

- Correspondence procedure

- Project document management procedure

- IT systems

- Contents of the Project Plan

- Specific quality and safety requirements

- For an integrated joint venture:

- Correspondence procedure

- Project document management procedure

- IT systems

- Contents of the Project Plan

- Budget, Cost control & forecasting system

- Underlying administrative system

- For a design subcontractor:

- Correspondence procedure

- Project document management procedure

- Design document management procedure

- IT systems

## During Tender Phase

Depending on the form of co-operation between partners, a minimum number of relevant project management procedures [tools], to be used after contract award, need to be agreed during tender stage.

The systems and procedures to be used during tender stage also need to be agreed between the partners.

System controlling documentation consists of:

- For a consortium partner:

- The Outline Project Co-ordination Plan

- For an integrated joint venture:

- The Outline Project Plan

- For a design subcontractor:

- The Outline Project Design Plan

- For a subcontractor:

- Conformance with the Outline Project Plan.  Specific important relevant procedures   	to be enclosed in the bid package.

## During Contract Phase.

System controlling documentation consists of:

- For a consortium partner:

- The Outline Project Co-ordination Plan

- For an integrated joint venture:

- The Outline Project Plan

- For a design subcontractor:

- The Outline Project Design Plan

- For a subcontractor:

- Conformance with the Project Plan.  Specific relevant procedures to be agreed in the subcontract.

# Attached documentation

None