# Purpose

The purpose of this procedure is to establish the various types of meetings, the typical participants, the typical agenda items and general aspects relevant to meetings.

# Scope

This procedure is applicable for all projects.

# Explanation of terms

AM:  	Area Manager

CE: 	Cost Engineer

CF:  	Circulation File.

DM:  	Design Manager

EM:  	Engineering Manager

HO:  	Head Office

PM:  	Project Manager

PQM:  	Project Quality Manager

PSM:  	Project Safety Manager

CM	Construction Manager

FA	Financial Administrator

QS	Quantity Surveyor

# Interface documentation

- Procedure Transfer Meetings [QU-P-10]

- Procedure Kick Off Meetings [QU-P-18]

- Procedure Correspondence and communication [QU-P-24]

# Responsibilities

In section 6 a table is enclosed which indicates the organiser of the meetings, the minimum attendance, the secretary who prepares the minutes and the distribution.

The organiser of the meeting shall prepare an agenda, appoint the secretary, invite the relevant parties and ensure that an agreement is made as to when the minutes will be ready and commented on [for regular meetings, the minutes will usually be discussed at the next meeting, for irregular meetings the organiser shall define the number of working days allowed for preparing the minutes, usually this is 3 days].

The secretary shall prepare and distribute the minutes in accordance with the agreements made [usually within 3 working days].

All participants to the meetings shall ensure that they are familiar with the minutes, have actioned the aspects agreed and attend the meeting in time.

# Description

Agenda items shall be prepared by the organisers.

Minutes of Meetings shall be issued for all formal meetings.

An action list of outstanding actions may be attached to the minutes.

The Minutes shall be issued in the English language and shall be coded in accordance with Procedure correspondence and communication [QU-P-24]

| Type of Meeting | Organiser of meeting & agenda | Frequency | Typical minimum attendance by | Secretary | Distribution |
| --- | --- | --- | --- | --- | --- |
| Internal progress meetings | PM | Every week | Key project personnel | Project Engineer | Key staff + AM |
| Progress/ problem information meetings | PM | Once every month | All staff | Project Engineer [notes] | Key staff + AM, CF |
| Progress meetings with Sub-contractors [per S/C] | CM | Once every week | Relevant key staff + S/C | Project Engineer | Key staff, CF |
| Progress Meetings with Client | Client | Once every fortnight | Client key personnel, PM, CM, EM | EM | Participants + AM, CF, HO |
| Design Meetings with Client | Project Manager | Once every fortnight | Clients relevant key personnel, PM, DM, | DM | Participants + AM, CF, HO |
| Quality Meetings with Client & other contractors | Client | Once every fortnight | Client’s relevant key personnel. SHANFARI TRADING AND FURNISHING CO. LLC’s PM, PQM | Client | Participants + PM, CM, CF |
| Safety meetings with Client & other contractors | Client | Once every fortnight | Client’s relevant key personnel. SHANFARI TRADING AND FURNISHING CO. LLC’s PM, PSM | Client | Participants + PM, CM, CF |
| JV Board Meetings | AM | Every 3 months | JV Board members + key project staff as required. | AM | JV Board + PM |
| Progress Meetings Area Manager/ Project Manager |  | Every two months | AM + PM | PM [notes suffice] | AM/ PM |
| Design Meetings with design subcontractor[s] | DM | Once every fortnight | Key personnel from design subcontractor[s] + PM, DM, EM | DM | Participants + AM |
| Transfer Meetings |  | As required | As per procedure QU-P-21 |  |  |

| Kick Off Meetings |  | As required | As per procedure QU-P-22 |  |  |
| --- | --- | --- | --- | --- | --- |
| Quarterly Report Meeting | EM | Every 3 months | PM, EM, DM, CM, QS, FA, CE | CE | Participants |

# Attached documentation

None.