# Purpose

This procedure gives an overview of the procedures and work instructions, which together form the Quality Control System on projects.

# Scope

All construction activities are subject to inspection & tests to confirm that a particular process has been satisfactorily completed and that the construction works may continue.

# Explanation of terms

None.

# Interface documentation

- Example Management of Quality Control Plan [QU-E-09]

- Work instruction for the Preparation of Inspection and Test Plan [QU-W-01]

- Work instruction Inspection & Inspection Reporting [QU-W-02]

- Work instruction Material Traceability [QU-W-03]

- Procedure Control of Non-conformities and Corrective Action [QU-P-27]

- Procedure Control of Project Quality Records [QU-P-26]

- Work instruction Vendor Assessment / Audit [QU-W-06]

- Procedure Archiving [QU-P-14]

# Responsibilities

The Project Quality Manager is responsible for all Quality Assurance and Quality Control matters of the project.

Detailed responsibilities are described in the various procedures and work instructions.

# Description

## Preparation of ITP

The various inspection activities shall be identified and controlled by means of Inspection & Test Plans, which indicates the stages at which an inspection or test is required and the type of test to be performed, see Work Instruction Preparation of Inspection & test Plan [QU-W-01].

## Inspection and Inspection Status

The status of inspections and tests shall be monitored by means of test reports and summary sheets or control logs. Control logs are prepared for all inspection and test activities and on the logs progress is being indicated, see Work instruction Inspection & Inspection Reporting [QU-W-02].

## Material Inspection

All materials at Suppliers, Subcontractors, Pre-fabrication yards and construction sites need to be inspected, handled, marked, documented, stored and preserved in a planned and systematic manner in accordance with project requirements.  These activities are described in the Work instruction Control of Material [EPC]  [QU-W-03].

## Non-conformities, corrective and preventive actions

Non-conformities are dealt with in accordance with Work instruction Non Conformance & Corrective Action Request [QU-W-04].

## Adjustment and calibration of inspection, test and measuring equipment

All measuring and test equipment shall be properly maintained, and where appropriate calibrated at regular intervals.

Calibration shall be based upon internationally recognised standards.  In case such standards do not exist, verification shall be based on manufacturer’s recommendations, checks and tolerances. Specific requirements shall be maintained in the Site Laboratory.

See also Procedure control of setting out and measuring equipment [QU-P-04]

## Quality records

Quality records are maintained in accordance with the Work instruction Quality Records [QU-W-05].

## Hand over documentation

As soon as possible, the Project Manager, Project Quality Manager, Engineering Manager, Document Controller shall prepare and agree with the Client the instruction Final Documentation.

Various quality documents can then already be stored in such a way that the documents are fit for submission to the Client at the end of the project

## Archiving

At the end of the project, the Project Quality Manager shall hand over the quality documentation to the Project Manager [ISO obligation to retain for 5 years] See Procedure Archiving [QU-P-14].

## Personnel and procedure qualification

When qualification of procedures or personnel is required by applicable regulations, codes, specifications or procedures, Contractor shall submit to Employer copies of valid Certificates or in the absence of same shall perform the qualification test in the presence of Client’s QC Inspector and submit the qualification record to Employer. Client’s QC inspector and or supervisor shall witness the test and / or review the record when deemed necessary.

# Attached documentation

None.