# Purpose

The purpose of this instruction is to ensure that all Requests For Information generated within a project are coded, recorded and answered within a specified time period.

# Scope

This Instruction covers all queries of a technical, procedural or contractual nature and is not to be used for personal or administration queries.

# Definitions

RFI	Request For Information
A technical, procedural or contractual query raised by
one party within a project for resolution by another party within the project.

# Responsibilities

It is the responsibility of all parties to register outgoing RFI’s as well as incoming RFI’s and to expedite the answers.

# Method

Queries shall be detailed on the Request For Information Form QU-F-05.

Only one query shall be raised under each Request For Information. i.e. only one query on each form.

The RFI shall be a "stand alone" document and shall be faxed to the recipient/originator without a transmittal or front sheet and shall not be treated as a fax.

No stamps for distribution shall be placed on the RFI.

The RFI shall be numbered with a sequential originator/recipient code [see procedure “Correspondence/ Communication Procedure”], i.e.:

A RFI shall only be coded by the originator. The recipient shall return the “original” RFI.

The originator shall:

- specify the query

- number, sign and date the RFI form

- enter the required response time

- enter details of reference documents and/or attachments, if any

- register the RFI on the outgoing Request For Information Register

- issue the RFI by fax to the addressee

- file the RFI in numerical order

- monitor progress on the outstanding RFI’s and expedite the response time as necessary

The recipient shall:

- register the RFI on the incoming Request For Information Register

- complete the RFI within the required response time

- return the RFI by fax to the originator

- register in the Request For Information Register the actual return date.

- file the RFI in numerical order