# Purpose

This work instruction presents an outline of the documentation required to be handed over to an EPC Client at the completion of a project.

# Scope

This work instruction should be adapted to suit specific project requirements. Considerable differences in final project documentation will exist depending on type of project and Clients requirements.

# Explanation of terms

Client:	.

Contractor:		SHANFARI TRADING AND FURNISHING CO. LLC

Manufacturing	The manufacturing databook represents a compilation of all databook:	documents which describe the asbuilt condition of the project.

# Interface documentation

- Procedure Control of Project Quality Records [QU-W-26]

- Work instruction Document Coding [QU-W-09]

# Responsibilities

The handover documentation will be compiled as work proceeds. The Manufacturing databook will be compiled, indexed and handed to the Client, once a specific structure is completed. Completion of the manufacturing databook for handover shall be finalised within 2 months of handover of the structures.

The following individuals shall coordinate the compilation of the manufacturing databooks, and they shall undertake the tasks assigned to them.

## Project Manager

- Has overall responsibility for ensuring that the manufacturing databook is correctly compiled and handed-over to Client.

- Issues a 'liens and claims release letter' indicating construction changes, which are still to be agreed [project specific requirement].

## Engineering Manager

- Preparation of as-built documentation incorporating all Engineering Instructions/Field Instructions.

- Preparation of punchlist prior to handover of the structure.

## Project Quality Manager

- Compilation of all original inspection and test records.

- Compilation of personnel certification records

- Close-out of all NCR and concession requests

- Preparation of inspection release certificate

- Compilation of all vendor handover documentation

## Document Controller

- Compilation of manufacturing databook comprising all original records.

- Producing requisite number of certified copies of manufacturing databooks.

- Transmittal of original manufacturing databook and requisite copies to Client.

- Preparing and archiving 2 copies of manufacturing databooks for Contractor.

# Description

The manufacturing databook is divided into nine sections, compiled on a work package basis using refinery facility codes.

Section 1 GENERAL

  - Contractual Scope of Work

  - Project [Quality and Safety] Plan [latest edition]

  - Engineering Studies I Technical Requisitions

    - General

    - Construction Jetty

    - Bulk Cargo Jetty

    - Intake Basin

    - Intake and Outfall Pipelines and Structures

  - Vendor Design Documents / Technical Proposals

  - Comprehensive Cross Referenced Index

Section 2 PERSONNEL AND EQUIPMENT CERTIFICATION

  - Welder Certification and Records

  - NDT Technician Qualification

  - Diving Inspection Qualification

  - Authorised Signatures and Inspection Stamps

  - Testing Equipment Certification

Section 3 TECHNICAL QUERIES

  - Non Conformance Reports

  - Concession Requests

  - Corrective Action Requests

  - Project Note Agreements

  - Engineering Instructions

  - Field Instructions

Section 4 MATERIAL PROCUREMENTAND CERTIFICATES

  - Piles Manufacturing Data Record

  - Pile Jackets Manufacturing Data Record

  - Testing Reports of Rebar Material

  - Welding Electrodes Certificate

  - Painting and Coatings Certificate

  - Concrete / Grout Mix Design

  - Laboratory Testing Reports

    - Raw Material Testing Reports

    - Cube Compressive Strength Test Reports

  - GRP Pipes Manufacturing Data Record

  - Navigation Aids Manufacturing Data Record

  - Fenders Manufacturing Data Record

  - Sacrificial Anodes Manufacturing Data Record

  - Miscellaneous

Section 5 GENERAL PROCEDURES

  - List of Contractor Procedures and Specifications

  - Sub-Contractor Procedures

    - Welding Procedure

    - Painting Procedure

    - Pile Testing Procedures

      - Preliminary Compression Load Test

      - Preliminary Tension Load Test

      - Permanent Pile Load Test

      - Pile Dynamic Analysis (P.D.A.)

    - Non Destructive Test Procedures

    - Welding General Material Control Procedure

    - Inspection and Test Plans

Section 6 Construction Jetty

  - Construction Procedures / Method Statements

  - Inspection and Testing Reports

  - As Built Drawings

  - Punch List

Section 7 Bulk Cargo Jetty

  - Construction Procedures Method Statements

  - Field Piles Fabrication Summary

    - Daily Welding Reports

    - Visual Inspection Reports

    - Dye Penetrant Inspection Reports

    - Ultrasonics Testing Reports

    - Straightness Reports

    - Painting Repair Reports

  - Jacket Driving, Grouting, Sacrificial Anodes Summary

    - Jacket Driving

      - Inspection Certificate Index - Jacket Driving

      - Jacket Driving Reports

    - Jacket Grouting

      - Inspection Certificate Index - Jacket Grouting

      - Jacket Grouting Reports

    - Sacrificial Anodes

      - Inspection Certificate Index - Sacrificial Anodes

      - Sacrificial Anodes Reports

    - Civil Work

      - Inspection Certificate Index - Civil Work

      - Inspection and Testing Reports - Civil Work

    - Miscellaneous Steel

      - Inspection Certificate Index - Miscellaneous Steel

      - Inspection and Testing Reports - Miscellaneous Steel

  - As Built Drawings

  - Punch List

Section 8 Intake Basin

  - Construction Procedures / Method Statements

  - Civil Work

    - Inspection Certificate Index - Civil Work

    - Inspection and Testing Reports - Civil Work

  - Miscellaneous Steel

    - Inspection Certificate Index - Miscellaneous Steel

    - Inspection and Testing Reports - Miscellaneous Steel

  - As Built Drawings

  - Punch List

Section 9 Intake and Outfall Pipelines and Structures

  - Construction Procedures / Method Statements

  - Inspection and Testing Reports

    - Intake Pipelines and Structures

      - On-Shore GRP Spools Assembly

      - Underwater GRP Spools Assembly

      - Backfilling of Trench Area

    - Outfall Pipelines and Structures

      - On-Shore GRP Spools Assembly

      - Underwater GRP Spools Assembly

      - Backfilling of Trench Area

  - Miscellaneous Steel

    - Inspection Certificate Index - Miscellaneous Steel

    - Inspection and Testing Reports - Miscellaneous Steel

  - As Built Drawings

  - Punch List

Once the manufacturing databook is complete and compiled the Contractor shall copy all documents and compile copies which contain all information contained in the Master original. Each original document shall be stamped, in red, with the word ‘ORIGINAL’ in a space which does not obscure the contents of the document; each copy shall be stamped with the ‘TRUE COPY OF ORIGINAL’, in red, also in a space which does not obscure the contents of the copy.

The distribution of the documents shall be as follows:

- Original and two certified copies to be sent to CLIENT.

- One certified copy to Joint Venture partner.

3.	One certified copy to be retained by SHANFARI TRADING AND FURNISHING CO. LLC.

# Attached documentation

- Attachment A: Refinery Facility Codes

Attachment A: Refinery Facility Codes

- Summary

Technical documents, which are to be delivered under this contract, require numbering in accordance with OWNER'S specification. This numbering system is specified in 'Work instruction document coding [QU-W-09].and this attachment is a synopsis of that system to include only those codes relevant to the contract.

- Numbering of Document

A2.1.	The OWNER document number has the format:

| X |  | 400 |  | ## |  | ## |  | ###X | [####] | Rev. X |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| [1] |  | [2] |  | [3] |  | [4] |  | [5] | [5’] | [6] |

These codes are as follows :

(1) Document Category Code

(2) Contract Code - 400 for this project

(3) Facility Code

(4) Document Classification Code

(5) Sequential Number with suffix

(5') Serial Number for Supplier Document

(6) Revision Number (0, A, B, C etc)

A2.2.	Document Category Codes

Applicable Document Category Codes are

Code 	Documents

S 	Equipment List Line List

Data Sheets

Reports

D	Drawing

Schedule

C	Calculation Sheet

R	Requisition

P		Procedure

L		Suppliers List / Sub-contractor List

E		Pre-order evaluation package

V		Supplier Document

A2.3. 	Refinery Facility Code

Utilities

53 	Cooling Water System

Marine Facilities

82 	Berthing Facilities

83 	Marine Navigational Facilities

86 	Refinery Bulk Cargo Jetty

A2.4 	Document Classification Codes

General

00 	Drawing Indexes / Procedures

01 	General Plot Plans / Key Plans

02 	As Built Programme Schedule

Equipment

10	Miscellaneous Equipment

Civil

41 	Site Preparation

42 	Piling

43 	Civil substructures and foundations

44 	Concrete substructures

45 	Underground Services

46 	Steel works Superstructures

47 	Buildings - Architecture

48 	Building Services

49 	Building - Structures

Piping

51 	Piping GA's / Key Plans

52 	Piping Isometric Detail drawings and indexes

54 	Misc. Piping drawings

58 	Misc. Pipe support drawings / details

Electrical

73 	Electrical (all documents)

Miscellaneous

91 	Spare Parts

99 	Miscellaneous